# Statement of Work

## GuardQuote: Secure Web Application with On-Premise Integration

| Name of Project | GuardQuote: Secure Web Application with On-Premise Integration |
| --- | --- |
| Project Lead/Contact | Malachi (malachite@my.csun.edu) |
| Sponsor | [Professor Name] |
| Project Manager | Rafa (rafael.garcia.498@my.csun.edu) - CI/CD & ML Automation |
| Domain/Web Presence | guardquote.ai (Cloudflare managed DNS & TLS) |
| Project Board | https://kuirbgs-team.monday.com/boards/9989927305 |
| Google Drive Repository | https://drive.google.com/drive/folders/1TQnaQzFNkjftctBFaWriesniiYME4zYp |

## Team Members

| Role | Name | Email |
| --- | --- | --- |
| Project Lead | Malachi | malachite@my.csun.edu |
| Cloud Infrastructure | Malachi | malachite@my.csun.edu |
| SIEM & Security Operations | Isaiah Bernal (klerky) | isaiah.bernal.415@my.csun.edu |
| Infrastructure & Networking | Xavier Nguyen (xan) | xavier.nguyen.000@my.csun.edu |

# I. Introduction

## Background

GuardQuote is a capstone project for CIT 480 that develops a comprehensive web platform for businesses to request network and security solution quotes. The project integrates AWS cloud infrastructure with on-premise Active Directory and SIEM systems, demonstrating enterprise-level security architecture with hybrid connectivity, defense-in-depth controls, and comprehensive logging and monitoring capabilities.

## Purpose

Demonstrate mastery of cloud infrastructure, identity management, CI/CD automation, and security operations through a production-ready system that integrates all team members' specialized domains while maintaining secure, high-availability architecture. The system showcases real-world security practices including zero-trust architecture, multi-factor authentication, threat detection, and incident response automation.

## Objectives

Build a multi-tier AWS VPC infrastructure with 3-tier subnet architecture across 2 availability zones

Implement perimeter security controls (WAF, security groups, IDS/IPS)

Integrate on-premise Active Directory for identity and access management

Achieve high availability with automatic failover and multi-AZ redundancy

Establish comprehensive logging and monitoring via CloudWatch and OpenSearch SIEM

Demonstrate security controls through penetration testing and incident response

Maintain cost optimization using ARM-based instances and managed services

Deliver complete documentation, architecture diagrams, and demo materials

# II. Scope of Work

## In Scope

AWS infrastructure (VPC, ALB, WAF, EC2/ECS, RDS, CloudWatch)

Network architecture with DMZ and private tiers

Security implementation (WAF rules, security groups, TLS/encryption)

IDS/IPS deployment with Suricata and traffic mirroring

SIEM integration with OpenSearch/Kibana for log aggregation

Active Directory authentication integration (AWS Managed AD)

Monitoring dashboards, alerts, and CloudWatch configuration

Security testing and vulnerability assessment

Operational documentation and deployment runbooks

Demo video and final presentation materials

## Out of Scope

Application development (existing app deployed)

On-premise infrastructure setup (assumed existing)

Custom IDS/IPS rule development beyond baseline rulesets

24/7 production operations and support

Production traffic migration and cutover

# III. Location

| Primary | AWS us-west-2 region (cloud-based infrastructure) |
| --- | --- |
| Secondary | On-premise (optional Phase 2: Active Directory and SIEM integration) |

# IV. Schedule

## Timeline Overview

| Phase | Start | Finish |
| --- | --- | --- |
| Phase 1: Network & DMZ | Week 1, Day 1 | Week 1, Day 2 |
| Phase 2: Load Balancer, WAF, Application | Week 1, Day 3 | Week 2, Day 1 |
| Phase 3: Database, Security Groups, AD | Week 2, Day 2 | Week 2, Day 4 |
| Phase 4: IDS/IPS, SIEM, Logging | Week 3, Day 1 | Week 3, Day 3 |

## Critical Path Dependencies

Network & DMZ must be operational before all other infrastructure phases

Load Balancer required before Web Application deployment

Security Groups necessary for proper tier isolation

Database and AD must be ready before application integration

IDS requires Traffic Mirroring from web tier (web tier must be deployed first)

SIEM is final integration point requiring all other components logging

# V. Resources Needed

| Item | Resource | Owner/Responsibility | Timeline |
| --- | --- | --- | --- |
| AWS Account | EC2, RDS, ECS, ALB, WAF, Secrets Manager, CloudWatch | Malachi (Infrastructure) | 3 weeks |
| Active Directory | Domain controller, LDAP/Kerberos services | Isaiah (SIEM/Identity) | 3 weeks |
| CI/CD Pipeline | GitHub Actions, Docker, Python/FastAPI | Rafa (CI/CD & Automation) | 3 weeks |

# VI. Deliverables

| Deliverable | Description | Due Date |
| --- | --- | --- |
| Deployed Infrastructure | Fully functional AWS environment with VPC, subnets, ALB, WAF, RDS, ECS/EC2, AD, IDS, SIEM | Week 3, Day 3 |
| Technical Documentation | Network diagrams, DFD L0/L1/L2, security architecture, configuration guides | Week 3, Day 4 |
| Security Validation Report | OWASP ZAP scan, penetration testing, IDS alerts, SIEM dashboards, demo video | Week 3, Day 5 |

# VII. Milestones

| Milestone | Start Date | Finish Date |
| --- | --- | --- |
| VPC and network infrastructure operational | Week 1, Day 1 | Week 1, Day 2 |
| Application deployed with AD authentication | Week 2, Day 1 | Week 2, Day 3 |
| IDS/SIEM operational with all sources logging | Week 3, Day 1 | Week 3, Day 3 |

# VIII. Tasks

| Task | Duration | Owner |
| --- | --- | --- |
| Network topology design, VPC/subnet creation, security group configuration | 3 hours | Malachi |
| ALB and WAF deployment, SSL/TLS certificate management | 2 hours | Malachi |
| Application containerization, ECS/EC2 deployment, CloudWatch agent | 4 hours | Rafa |
| RDS provisioning, encryption, Secrets Manager integration | 2 hours | Malachi |
| Active Directory setup, LDAP authentication integration | 2 hours | Isaiah |
| Suricata IDS deployment, traffic mirroring, rule tuning | 3 hours | Isaiah |
| OpenSearch/Kibana setup, log ingestion pipeline, dashboards | 3 hours | Isaiah |
| Security testing (OWASP ZAP, penetration testing) | 2 hours | Isaiah |
| Documentation writing, architecture diagrams | 2 hours | Team |
| Demo video recording, final validation | 3 hours | Team |

# IX. Standards and Testing

## Reporting and Communications

Weekly 30-minute standup meetings; Slack channel for async updates; GitHub PR reviews; shared Google Drive for documentation; final presentation to course instructor.

## Testing & Acceptance Criteria

| Standard | Owner | Due Date |
| --- | --- | --- |
| Website accessible via HTTPS with valid TLS certificate | Isaiah | Week 3, Day 2 |
| Multi-AZ failover tested: infrastructure survives single AZ failure | Malachi | Week 3, Day 3 |
| All OWASP Top 10 attack patterns blocked by WAF | Isaiah | Week 3, Day 3 |
| IDS generates alerts on simulated attacks within 2 minutes | Isaiah | Week 3, Day 3 |
| All logs aggregated in SIEM with <5 minute latency | Isaiah | Week 3, Day 4 |
| Active Directory authentication working for application users | Isaiah | Week 3, Day 3 |
| CloudWatch alarms trigger on critical conditions | Malachi | Week 3, Day 4 |

# X. Define Success

Project is successful when:

Website is accessible via HTTPS with valid TLS certificate and security headers

All OWASP Top 10 attack patterns are blocked by WAF

Multi-AZ deployment survives single AZ failure without service interruption

All logs aggregated in SIEM with latency under 5 minutes

IDS detects and alerts on attack signatures in near real-time

Active Directory authentication integrated and functional for all users

CloudWatch monitoring and alarms active for all critical metrics

Complete technical documentation and demo video delivered

Final presentation demonstrates security architecture to instructor

# XI. Requirements

## Equipment & Access

AWS account with appropriate service limits (free tier eligible)

Laptop with Docker, Git, Python, and AWS CLI

Access to GitHub repository and Google Drive shared folder

Cloudflare domain (guardquote.ai) with DNS management

## Certifications & Training

ucertify Mastering Windows 2022 (pending professor donation/approval)

## Skills & Knowledge

Linux/Ubuntu command line

Networking concepts (VPC, subnets, routing, firewalls)

Cloud architecture and AWS services

Active Directory/LDAP authentication

SIEM and security operations concepts

GitHub and CI/CD pipelines

# XII. Other

## Cost Management

Infrastructure cost-optimized using t4g ARM instances and managed services. Approximately $312/month demo environment. All resources tagged for cost tracking with billing alarms configured.

## Cloudflare Configuration

Domain: guardquote.ai

DNS Management: Enabled

TLS/SSL Certificate: Cloudflare managed (automatic renewal)

WAF Provider: Cloudflare WAF + AWS WAF (dual-layer)

Rate Limiting: Enabled

DDoS Protection: Standard (included)

# XIII. Payments & Costs

| Service | Cost | Payment Schedule |
| --- | --- | --- |
| AWS Services (EC2, RDS, ALB, WAF, ECS, Managed AD) | ~$312/month (demo, free tier 12mo) | Monthly billing |
| Third-party Tools (Suricata, OpenSearch, Kibana open-source) | $0 | N/A |

# XIV. Closure

| Document | Sign-Off |
| --- | --- |
| Final technical documentation and architecture diagrams | Instructor approval |
| Demo video and security testing report | Team review + Instructor approval |
| Operational runbook and lessons learned | Team review completed |

Project Board: https://kuirbgs-team.monday.com/boards/9989927305 | Drive: https://drive.google.com/drive/folders/1TQnaQzFNkjftctBFaWriesniiYME4zYp